## Bid comparison
Condo / HOA bid comparison sheet
Project: | 48-unit condo roof replacement (example - replace with yours)
Association:
Prepared by / date:
Item | Bidder A | Add for A | Bidder B | Add for B | Bidder C | Add for C | What to check
Price on the bid | 186400 |  | 162900 |  | 191250 |  | Copy the total exactly as printed.
WHAT THE PRICE COVERS (Included / Left out / Not mentioned)
Tear-off and disposal | Included |  | Included |  | Included |  | All layers, or only the top one?
Rotten deck boards | 20 sheets incl. |  | Not mentioned | 9500 | 40 sheets incl. |  | Ask for a price per sheet in writing.
Permits | Included |  | By owner | 4800 | Included |  | "By owner" means the association pays.
Resident protection and cleanup | Included |  | Not mentioned | 7500 | Included |  | Daily cleanup, magnet sweep, landscaping.
Flashing, vents and drains | Included |  | Included |  | Included |  | New metal, or reused?
Workmanship warranty | 10 years |  | 2 years |  | 5 years |  | Who fixes leaks after the warranty ends?
Manufacturer warranty | Registered, 25 yr |  | Not mentioned |  | Registered, 20 yr |  | Is it registered in the association's name?
CHECKS BEFORE THE VOTE
Licence number checked | Yes |  | Yes |  | Yes |  | Look it up on your state or provincial register.
Insurance names the association | Yes |  | Asked |  | Yes |  | Certificate lists the association as additional insured.
Workers' compensation | Yes |  | Asked |  | Yes |  | Ask for the certificate, not a promise.
Deposit | 10% |  | 50% |  | 15% |  | A large deposit before work starts is a risk.
Payment schedule | By stage |  | On completion |  | By stage |  | Pay as work is done and inspected.
Start and finish dates | Jun 2 - Jun 27 |  | Not mentioned |  | Jun 9 - Jul 3 |  | Write dates into the contract.
Price for extra work | $85/hr + materials |  | Not mentioned |  | $90/hr + materials |  | Agree the rate before work starts.
References from similar buildings | 2 condos |  | None given |  | 3 condos |  | Call at least one.
Board member ties to bidder | None |  | None |  | None |  | Record any relationship before the vote.
Missing work priced in
Price once gaps are added | [6 empty] | Compare these, not the printed prices.
QUESTIONS TO SEND EACH BIDDER (in writing)
Bidder A
Bidder B
Bidder C
Board recommendation and reasons

## How to use
1 | Get bids for the same work. Send every contractor the same scope.
2 | Copy each price exactly as printed into "Price on the bid".
3 | For each item, write Included, Left out or Not mentioned. A blank is not a yes.
4 | When a bid leaves an item out, put a fair amount in that bidder's "Add for" column.
5 | Compare "Price once gaps are added", not the printed prices.
6 | Check licence, insurance, deposit, payment schedule and warranty for every bidder.
7 | Record any relationship between a board member and a bidder before the vote.
8 | Send each bidder your questions in writing and keep the answers with this sheet.
Rather not type? Upload the bids at estimatehawk.com/check-my-bids/ for a free check.
The $9 report adds a one-page board summary PDF with the page each fact came from.